## Slide 1
Institution-Wide Initiatives and Projects: Lessons Learned from an LMS Migration
Anthony Piña, Todd Smoak & Christopher Brandt

## Slide 2: Background
During 2022-23, ISU implemented a successful LMS transition from Sakai (ReggieNet) to Canvas.
What were the contributors to the project’s success and what were the challenges and pain points?

## Slide 3: Objectives
Determine what large-scale technology initiatives and projects need to be successful
Discuss the challenges of large-scale technology initiatives
Discuss the lesson learned and implications of large-scale technology initiatives and projects

## Slide 4: Large-Scale Technology Initiatives
Involves personnel and resources throughout the organization
Scope and beneficiaries not limited to a single organizational unit (e.g., program or college)
Requires a comprehensive organizational and operational structure

## Slide 5: Setting Up Organization for Success
Steering committee
Leadership
Project management
Task forces and working groups

## Slide 6: Steering Committee
High-level decision makers
  Authority to allocate funds and personnel
  Ties initiative to mission & strategic plan
  Determines metrics for success
  Provides accountability to chief executives
  “Over-arching” decision-making
  Not too involved in minutiae or micro-management

## Slide 7: Leadership
The “face” of the project
  Reports to the Steering Committee
  Promote project across and/or outside the organization
“Daily” (operations) decision-making
  Coordinates/leads daily operations
  Configurations, policy, procedures, training, support
  Gathers and reports data

## Slide 8: Project Management
Too often neglected
Provides accountability
  Works closely with leadership to make sure that all tasks are completed
  Identifies gaps and redundancies
  Keeps project on track

## Slide 9: Project Management Triple Constraint

## Slide 10: Task Forces and Working Groups
“Boots on the ground”
  Steering, Leaders & Project Managers can’t do everything
Opportunities for inclusiveness
  Included stakeholders, end users & support staff
Performed pilot testing & formative evaluation
  Made recommendations to leadership

## Slide 11: Challenges
Personnel changes (leadership, project manager)
Issues with 3rd party vendors (LTIs, migration timelines)
A few product technical issues (e.g. quizzes)
Vendor guidance better for teaching than for admin
Not all users were 100% satisfied
  Small minority preferred the old system

## Slide 12: Successes of LMS Initiative
Project implemented in an expedited timeline
Broad coalition (students, faculty, staff, administration)
High-level of end-user satisfaction
Improved working relationships
  e.g., addressing redundancies between TSC and CIPD

## Slide 13: Successes of LMS Initiative
Implemented policies and procedures to improve existing operations
Configurability of the product worked very well
Overall, Instructure has been a good vendor partner
We were effective in decision making & adaptation
  We had to adjust our integrations with 3 revisions

## Slide 14: Lessons Learned and Implications
Change will happen! Put people & processes in place
Need to be able to make timely decisions
Get the right people in the right positions
Do not skimp on these organizational functions
Clear and shared vision across the institution
  Communication is vital

## Slide 15
Institution-Wide Initiatives and Projects: Lessons Learned from an LMS Migration
Anthony Piña, Todd Smoak & Christopher Brandt